## Summary
35th Avenue Innovation Corridor Improvements, City of Phoenix
Benefit-Cost Analysis
Analysis Period: 2024-2044 | 7% Discount Rate
Costs (2017 $M)
Capital Cost | 18.5796
Total Costs | 18.5796
Benefits (2017 $M)
Safety Benefits
Reduced Roadway Fatalities and Crashes | 24.8323
Sub-Total | 24.8323
Environmental Sustainability Benefits
Emission Savings | 0.038616
Sub-Total | 0.038616
Economic Competitiveness Benefits
Travel Time Savings | 14.0296
Sub-Total | 14.0296
State of Good Repair Benefits
Residual Savings | 1.141
Sub-Total | 1.141
Net Operating & Maintenance Costs | -0.62756
Total Benefits | 39.4139
Outcome
Net Benefits (2017 $M) | 20.8343
Benefit-Cost Ratio | 2.1214
Project Description
The 35th Avenue Innovation Corridor is a comprehensive infrastructure improvement project that will transform the corridor into a safe and efficient route for commuters and students.
The project implements a series of improvements that target current pedestrian and vehicular safety concerns throughout the corridor. The project takes an innovative approach to addressing safety concerns by incorporating traffic management strategies in conjunction with safety countermeasures to ultimately create a safe, attractive, and efficient corridor for all modes of transportation.
Proposed Improvements include:
Signalized Mid-Block Crossings
Street Lighting
Center Medians
Intersection Rebuild
Fiber Optic Cables
Signal Timing/Progression Speed
Pavement Maintenance

## Inputs
Benefit Cost Analysis Inputs
35th Avenue Innovation Corridor Improvements, City of Phoenix
Input | Value | Source
General
Discount Rate | 7% | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs | https://www.transportation.gov/sites/dot.gov/files/docs/mission/office-policy/transportation-policy/14091/benefit-cost-analysis-guidance-2018.pdf
Deflator for converting $ values to 2017$ | See "Deflator" Sheet | https://www.whitehouse.gov/wp-content/uploads/2019/03/hist10z1-fy2020.xlsx
Base year dollar | 2017
Discount year | 2019
Annualization factor | 260 | Assumed to reflect weekday peak periods in a year
Vehicle occupancy | 1.32 | Average Auto Occupancy, 2019; MAG
Economic Competitiveness
Value of Time - Personal (2017$) | 14.8 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
Environmental Sustainability
VOC Value of Emissions (2017$) per short ton | 2000 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
N2O Value of Emissions (2017$) per short ton | 8300 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
PM2.5 Value of Emissions (2017$) per short ton | 377800 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
SO2 Value of Emissions (2017$) per short ton | 48900 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
CO2 Value of Emissions (2017$) per short ton | varies
VOC Emission Rates Per Hour (Weighted Average), g/hr | 3.0997 | Source: "Idling Vehicle Emissions for Passenger Cars, Light-Duty Trucks, and Heavy-Duty Trucks Emission Facts", EPA420-F-08-205, October 2008
THC Emission Rates Per Hour (Weighted Average), g/hr | 3.6037 | Source: "Idling Vehicle Emissions for Passenger Cars, Light-Duty Trucks, and Heavy-Duty Trucks Emission Facts", EPA420-F-08-205, October 2008
CO Emission Rates Per Hour (Weighted Average), g/hr | 58.8671 | Source: "Idling Vehicle Emissions for Passenger Cars, Light-Duty Trucks, and Heavy-Duty Trucks Emission Facts", EPA420-F-08-205, October 2008
N2O Emission Rates Per Hour (Weighted Average), g/hr | 3.6715 | Source: "Idling Vehicle Emissions for Passenger Cars, Light-Duty Trucks, and Heavy-Duty Trucks Emission Facts", EPA420-F-08-205, October 2008
CO2 Emission Rates Per Hour, g/hr | 2443.925 | Source: Greenhouse Gas Emissions from a Typical Passenger Vehicle, EPA
PM 2.5 Per Hour | 0.024293 | Source: Fact #861 February 23, 2015 Idle Fuel Consumption for Selected Gasoline and Diesel Vehicles; "Average Annual Emissions and Fuel Consumption for Gasoline-Fueled Passenger Cars and Light Trucks", EPA420-F-08-024, October 2008
PM 10 Per Hour | 0.026238 | Source: Fact #861 February 23, 2015 Idle Fuel Consumption for Selected Gasoline and Diesel Vehicles; "Average Annual Emissions and Fuel Consumption for Gasoline-Fueled Passenger Cars and Light Trucks", EPA420-F-08-024, October 2008
Conversion rate for Metric tons to Short Tons | 1.1015 | Source: 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
Grams Per Short Ton | 907185
Grams Per Metric Ton | 1000000
Safety
O – No Injury | 3200 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
C – Possible Injury | 63900 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
B – Non-incapacitating | 125000 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
A – Incapacitating | 459100 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
K – Killed | 9600000 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
U – Injured (Severity Unknown) | 174000 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
# Accidents Reported (Unknown if Injured) | 132200 | December 2018 Benefit-Cost Analysis Guidance for Discretionary Grant Programs
Partial-Year Benefits
2020 | 0
2021 | 0
2022 | 0
2023 | 0
2024 | 0.25 | operations begin Fall 2024
2025 | 1
2026 | 1
2027 | 1
2028 | 1
2029 | 1
2030 | 1
2031 | 1
2032 | 1
2033 | 1
2034 | 1
2035 | 1
2036 | 1
2037 | 1
2038 | 1
2039 | 1
2040 | 1
2041 | 1
2042 | 1
2043 | 1
2044 | 0.75
2045 | 0

## CapitalCosts_Summary
35th Avenue Innovation Corridor Improvements, City of Phoenix
Summary of Project Capital Costs
This table provides a summary of project costs by type and distribution by year based on the proposed construction schedule.
| 7% | Discount Rate
| 2019 | Discount Year
Project Cost Breakdown | Total (2019$) | Total (2017$) | Line Item to match Schedule | Start month-year | End month-year | Duration (months) | 2020 | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024
Pre-Design Study | 75000 | 71947.7519 | Design | 2020-01-01 | 2020-06-01 | 6 | 6 |  |  |  |  | 71947.7519 | 0 | 0 | 0 | 0
Design | 1929787.86 | 1851251.9759 | Design | 2020-07-01 | 2021-05-01 | 11 | 6 | 5 |  |  |  | 1009773.805 | 841478.1709 | 0 | 0 | 0
Design Administration | 1988870.29 | 1907929.9494 | Design | 2020-01-01 | 2021-05-01 | 17 | 12 | 5 |  |  |  | 1346774.0819 | 561155.8675 | 0 | 0 | 0
ROW Acquisition | 1993280 | 1912160.199 | ROW | 2020-06-01 | 2021-05-01 | 12 | 7 | 5 |  |  |  | 1115426.7828 | 796733.4163 | 0 | 0 | 0
Environmental | 200000 | 191860.6718 | Env | 2020-01-01 | 2020-11-01 | 11 | 11 |  |  |  |  | 191860.6718 | 0 | 0 | 0 | 0
Streetlights and Signals | 3666000 | 3516806.1134 | Utilities | 2020-06-01 | 2020-12-01 | 7 | 7 |  |  |  |  | 3516806.1134 | 0 | 0 | 0 | 0
T2050 Prior Rights Fee | 184184 | 176688.3298 | throughout length of the project | 2020-01-01 | 2024-09-01 | 57 | 12 | 12 | 12 | 12 | 9 | 37197.5431 | 37197.5431 | 37197.5431 | 37197.5431 | 27898.1573
Testing and Materials | 128652.524 | 123455.6407 | Construction | 2022-01-01 | 2024-09-01 | 33 |  |  | 12 | 12 | 9 | 0 | 0 | 44892.9603 | 44892.9603 | 33669.7202
Utility Adjustments | 643262.62 | 617083.992 | Utilities | 2020-06-01 | 2020-12-01 | 7 | 7 |  |  |  |  | 617083.992 | 0 | 0 | 0 | 0
Construction | 9199252.4 | 8827651.1318 | Construction | 2022-01-01 | 2024-09-01 | 33 |  |  | 12 | 12 | 9 | 0 | 0 | 3210054.957 | 3210054.957 | 2407541.2178
Construction Administration | 2717703.004 | 2607101.62 | Approvals | 2021-06-01 | 2021-11-01 | 6 |  | 6 |  |  |  | 0 | 2607101.62 | 0 | 0 | 0
| 22725992.698 | 21803937.3757
Year | Total Capital Costs (2017$) | Discounted Capital Total (7%)
2019 |  | 0
2020 | 7906870.7419 | 7389598.8242
2021 | 4843666.6177 | 4230646.0107
2022 | 3292145.4604 | 2687371.3497
2023 | 3292145.4604 | 2511562.0091
2024 | 2469109.0953 | 1760440.6606
2025 |  | 0
Total | 21803937.3757 | 18579618.8544

## CapitalCostEst
35th Avenue Innovation Corridor Improvements, City of Phoenix
Project Cost Estimate
This table provides a detailed list of what is included in the project capital costs.
| CD |  | STXXXXXXXX |  | Q.S. |  | Date
Construction | Qty | Unit | Unit Cost | Total Cost 18/19 | Total Cost 19/20 | Total Cost 20/21 | Total Cost 21/22 | Total Cost 22/23
REG CORNER ADA RAMP | 0 | EA | 2500 | 0
LIMITED ADA RAMP | 0 | EA | 1500 | 0
DUAL ADA RAMP | 0 | EA | 2500 | 0
MIDBLOCK RAMP | 0 | EA | 1500 | 0
RESIDENTIAL STREET ADA RAMPS | 0 | EA | 1500 | 0
TRUNCATED DOMES | 0 | SF | 35 | 0
SUBGRADE PREPARATION | 0 | SY | 5 | 0
EARTHWORK | 0 | CY | 20 | 0
AC PAVEMENT (SURFACE COURSE) | 0 | Ton | 85 | 0
AC PAVEMENT (BASE COURSE) | 0 | Ton | 80 | 0
SURFACE TREATMENT (MICRO/SLURRY) | 0 | SY | 4 | 0
TACK COAT | 0 | Ton | 850 | 0
AGGREGATE BASE COURSE | 0 | Ton | 20 | 0
RUBBERIZED ASPHALT CONCRETE BASE COURSE | 0 | Ton | 100 | 0
AC PAVEMENT & BASE | 0 | SY | 30 | 0
12.5 KV POLE RELOCATIONS | 0 | EA | 5000 | 0
17' CATCH BASIN, REMOVE EXISTING | 0 | EA | 17000 | 0
3' WALK BEHIND SIDEWALK | 0 | SF | 4.98 | 0
5 GALLON SHRUBS | 0 | EA | 20 | 0
8" DIP Waterline | 0 | LF | 160 | 0
ADJUST ELECTRICAL BOX | 9 | EA | 4800 | 43200 | electric light +power
ADJUST IRRIGATION BOX | 0 | EA | 350 | 0
ALLEY ENTRANCE | 0 | SF | 10 | 0
ARCHEOLOGY TRENCHING | 0 | EA | 3100 | 0
ASPHALT REMOVAL | 0 | SY | 1 | 0
BOX CULVERT | 0 | LF | 1710 | 0
BOX TREE 24" | 0 | EA | 600 | 0
BRIDGE, COMPLET W/CHNL, ETC (PER SF DECK) (I-BEAM BRIDGE) | 0 | SF | 130 | 0
BRIDGE, COMPLET W/CHNL, ETC (PER SF DECK) (DECK SLAB BRIDGE) | 0 | SF | 100 | 0
BUS BAY | 0 | EA | 16500 | 0
BUS SHELTER | 0 | EA | 3000 | 0
BUS BENCH | 0 | EA | 1300 | 0
BUS TRASH CAN | 0 | EA | 700 | 0
CATCH BASIN | 0 | EA | 4600 | 0
CATCH BASIN PIPE (See chart below) | 0 | LF | 75 | 0
CLEAR AND GRUB SITE | 0 | EA | 5000 | 0
CONCRETE APRONS | 0 | SF | 10 | 0
CONCRETE DRIVEWAY ENTRANCE | 0 | SF | 10 | 0
CONCRETE MEDIAN NOSE | 0 | SF | 13 | 0
CRACK SEAL | 0 | SY | 0.7 | 0
DECOMPOSED GRANITE | 0 | CY | 100 | 0
DECOMPOSED GRANITE FOR MAINTENANCE ROAD | 0 | CY | 120 | 0
FILL | 0 | CY | 7.67 | 0
FOUNDATION FOR SIGN POST | 0 | EA | 150 | 0
GUARDRAIL | 0 | LF | 25 | 0
GRADING | 0 | LS | 6500 | 0
HAWK SIGNAL | 3 | EA | 200000 | 600000 | telecommunications
HEADWALL INLET | 0 | EA | 4500 | 0
INSTALL RETAINING WALL WITH HAND RAIL | 0 | LF | 221 | 0
IRRIGATION MODIFY | 0 | EA | 2600 | 0
IRRIGATION PIPE | 0 | LF | 3 | 0
LANDSCAPING ( INCL PLANTS, IRRIG, GRANITE, ETC.) | 0 | SF | 6 | 0
LANDSCAPE CONTROLLER AND REMOTE CONTROL | 0 | EA | 500 | 0
LANDSCAPE WALL | 0 | LF | 130 | 0
MANHOLE ADJUST | 0 | EA | 470 | 0
MICROSEAL | 0 | SY | 7.59 | 0
MILLING |  | SY | 2 | 0
MULTI-USE PATH (DECOMPOSED GRANITE 3" THICK) | 0 | SF | 1 | 0
MULTI-USE PATH (4" CONCRETE) | 0 | SF | 4.5 | 0
OBLITERATING EXISTING PAVEMENT MARKINGS | 0 | LF | 1.1 | 0
OVERLAY (1.5") | 0 | SY | 7 | 0
PAVEMENT MARKING - SYMBOL | 0 | EA | 150 | 0
PAVEMENT MARKING - WHITE | 0 | LF | 0.4 | 0
PAVEMENT MARKING - YELLOW | 0 | LF | 0.4 | 0
POWER POLE | 0 | EA | 5000 | 0
RAPID FLASHING BEACON | 0 | EA | 100000 | 0
REGULATION SIGN PANELS | 0 | SF | 20 | 0
RELOCATE CHAIN LINK/WOOD FENCE | 0 | LF | 10 | 0
RELOCATE EXISTING MAILBOX | 0 | EA | 270 | 0
RELOCATE FIRE HYRANT | 0 | EA | 3000 | 0
RELOCATE SLIDING GATE | 0 | EA | 345 | 0
REMOVE CHAIN LINK FENCE | 0 | LF | 5 | 0
REMOVE CONCRETE D/W, S/W, VG, SLAB, ETC. | 0 | SF | 2 | 0
REMOVE DECORATIVE PAVERS | 0 | SF | 2.17 | 0
REMOVE EXISTING CATCH BASIN | 0 | EA | 670 | 0
REMOVE EXISTING MANHOLE AND BACKFILL | 0 | EA | 645 | 0
REMOVE VERT CURB & GUTTER, SINGLE CURB | 0 | LF | 6.5 | 0
REMOVE/REPLACE SPRINKLER HEADS | 0 | EA | 250 | 0
REMOVE STRUCTURE/BACKFILL AND COMPACT | 0 | EA | 16 | 0
RETAINING WALL | 0 | SF | 100 | 0
RETAINING WALL WITH HANDRAIL | 0 | LF | 221 | 0
ROLL CURB & GUTTER | 0 | LF | 20 | 0
SCUPPER | 0 | EA | 5000 | 0
SCUPPER WITH RAILING | 0 | EA | 5500 | 0
SIDEWALK 4FT LOCAL STREET (<1000SF $12) | 0 | SF | 4.5 | 0
SIDEWALK 5FT COLLECTOR STREET (<1000SF $14) | 0 | SF | 6.5 | 0
SIDEWALK 6FT MAJOR STREET (<1000SF $16) | 0 | SF | 8.5 | 0
SIGN POST (P-1)(PERFORATED)(SINGLE) | 0 | EA | 80 | 0
SINGLE CURB | 0 | LF | 20 | 0
SITE FURNISHING UPGRADES | 0 | EA | 13800 | 0
SLURRY SEAL | 0 | SY | 2.7 | 0
SRP IRRIGATION MANHOLE | 0 | EA | 9500 | 0
SRP IRRIGATION PIPE | 0 | LF | 240 | 0
STAMPED ASPHALT | 0 | SF | 6 | 0
STORM DRAIN MANHOLES - 500 FT SPACING | 0 | EA | 4000 | 0
STORM DRAIN CONNECT TO MANHOLE | 0 | EA | 8000 | 0
STORM DRAIN PIPE (See chart below) | 0 | LF | 180 | 0
STREETLIGHT - CONTINGENCIES | 60 | EA | 3600 | 216000 | electric light +power
STREETLIGHT - REMOVE/REPLACE WITH LED | 0 | EA | 500 | 0
STREETLIGHT TRENCHING/POWER/J-BOX | 15000 | LF | 40 | 600000 | electric light +power
SURVEY/UTILITY & ROW MAPPING/CONST DOCS 30% ROLL PLOT | 0 | EA | 9600 | 0
TRAFFIC SIGNAL INTERSECTION | 9 | EA | 250000 | 2250000 | telecommunications
TRAFFIC SIGNALS/BOX/LOOPS - Per Corner | 0 | EA | 88000 | 0
TRAFFIC SIGNAL RECONFIGURE | 0 | EA | 2000 | 0
TREE REMOVAL | 0 | LS | 880 | 0
TRENCH FRAMES & GATED COVERS | 0 | EA | 2500 | 0
UNDERGROUND 69KV/12KV POWER LINES | 9500 | LF | 300 | 2850000 | electric light +power
VALLEY GUTTER | 0 | SF | 10 | 0
VALVE BOX - WATER/IRRIGATION | 0 | EA | 2200 | 0
VERTICLE CURB & GUTTER | 0 | LF | 18 | 0
WATER MANHOLE ADJUSTMENT | 0 | EA | 383 | 0
WATER METER INSTALLATION | 0 | EA | 2350 | 0
WATER METER RELOCATE | 0 | EA | 710 | 0
WROUGHT IRON FENCE AND SLIDING GATE | 0 | LF | 50 | 0
INSTALL RAISED MEDIAN (150 ft length median) | 20 | EA | 30000 | 600000 | highways and streets
MILL & OVERLAY | 1 | MI | 900000 | 900000
INSTALL FIBER OPTIC CABLE | 3 | MI | 250000 | 750000 | telecommunications
INSTALL PERMANENT DRIVER FEEDBACK SIGNS | 20 | EA | 20000 | 400000 | telecommunications
Construction |  |  |  | 9209200
SWPP Allowance (.7%) |  |  | 0.7% | 64464.4
Misc Removal and other work (2%) |  |  | 2% | 184184
Mobilization (0% Local or Collector, 2% Major) |  |  | 2% | 184184
Traffic Control/Police Officer (1% Local, 4% collector, 5% major) |  |  | 5% | 460460
Allowance for Extra Work (0-10% of subtotal depending on site conditions) |  |  | 10% | 920920
Contingency (20%) |  |  | 20% | 1841840
Total Project Construction Cost |  |  |  | 12865252.4
Pre-Design/Study |  |  | 75000 | 75000
Design ($30K minimum local/collector, $50K minimum Major) |  |  | 15% of Construction | 1929787.86
DCM Design Administration Fee |  |  | 12% of Construction | 1543830.288
APS/SRP Design Fee (per mile / per side) | 2 | EA | 25000 | 50000
APS Construction Fee (per mile/ per side) | 2 | EA | 75000 | 150000
T2050 Street lighting Fee (T2050 projects only) | 2% |  | 2% of Construction | 184184
ADOT Design Review Fee (per segment) | 2 | EA | 10000 | 20000
PIO (See List Below) | Proj Division | 85 | 12000 | 12000
Procurement - Design | 2 | EA | 5000 | 10000
Project Handoff Admin - TPP/ENV/UTIL | 2 | EA | 6520 | 13040
State Land Acquisition | 0 | SF | 10 | 0
State Land Admin per property of State Land | 0 | EA | 17250 | 0
ROW Acquisition per square foot of land | 44000 | SF | 7.55 | 332200
Appraisal per property | 20 | EA | 2500 | 50000
Appraisal Admin per property | 20 | EA | 327 | 6540
Phase 1 Environmental per property | 20 | EA | 3000 | 60000
Title Service Reports per property | 20 | EA | 650 | 13000
Title Service Legals/Deeds per property | 20 | EA | 327 | 6540
Real Estate Admin per property (Collector, Major) | 20 | EA | 11750 | 235000
Real Estate Admin per property (Local) | 20 | EA | 7500 | 150000
Real Estate TCE Charge for Federal Aid projects | 20 | EA | 10800 | 216000
ROW Fee Title | 44000 | SF | 21 | 924000
ROW Easements (Local) | 0 | SF | 9 | 0
ROW Federal Aid Clearance | 2 | EA | 20000 | 40000
Temporary Construction Easement | 0 | SF | 1.5 | 0
Environmental Clearance | 3 | EA | 50000 | 150000
Environmental Monitoring/Archeology ($25K Local, $50K Collector, $100K Major) Use unless the Environmental section submits an estimate | 2 | Job | 100000 | 200000
DCM Construction Administration Fee (See list below) | Proj Type | 1 | 20% | 2573050.48
Procurement - Construction | 2 | EA | 8000 | 16000
Testing & Materials (1%) |  | EA | 1% of Construction | 128652.524
Utilities Adjustment (5%) |  |  | 5% of Construction | 643262.62
Utility Inspection |  |  | 1% of Construction | 128652.524
Inflation Increase per Year |  |  |  | 1
Project Grand Total |  |  |  | 22725992.696
Use the figures below to fill in Project Number Request form for Fiscal
Fiscal Year the work will be done - Use the correct column for the work below to calculate the total project cost. |  |  |  | Total Cost 18/19 |  | Total Cost 20/21 | Total Cost 21/22 | Total Cost 22/23 | GL
Pre-Design/Study |  |  |  | 75000 |  | 0 | 0 | 0 | 510033
Design (Consultant Contract) |  |  |  | 1929787.86 |  | 0 | 0 | 0 | 510030
Design Admin (Includes DCM, PIO, Design Procurement, APS/SRP Design Fee, TPP staff time) |  |  |  | 1988870.29 |  | 0 | 0 | 0 | 510060
ROW (Acquisition/Adm) |  |  |  | 1993280 |  | 0 | 0 | 0 | 532000
Environmental |  |  |  | 200000 |  | 0 | 0 | 0 | 510155
Streetlights and Signals |  |  |  | 3666000 |  | 0 | 0 | 0 | 510137
T2050 Prior Rights Fee |  |  |  | 184184 |  | 0 | 0 | 0 | 510141
Testing & Materials (1%) |  |  |  | 128652.524 |  | 0 | 0 | 0 | 510175
Utility Adjustments |  |  |  | 643262.62 |  | 0 | 0 | 0 | 510140
Construction |  |  |  | 9199252.4 |  | 0 | 0 | 0 | 510130
Cons Admin (Includes DCM, Construction Procurement, Utility Inspection, ADOT Review Fee) |  |  |  | 2717703.004 |  | 0 | 0 | 0 | 510060
|  |  | Total | 22725992.698 |  | 0 | 0 | 0
Construction Admin Fee by project type | Enter number into C163 | % |  | Taper
Major Street | 1 | 20% |  | Speed Limit | Formula |  |  | ASPHALT |  | ABC
Bridges | 2 | 15% |  | 40 or Under | L = WS^2/60 |  |  | Surface | Base | 3
Storm Sewers | 3 | 17% |  | 45 or Over | L = WS |  |  | 1.5 | 6
Drainage Channels/Basins | 4 | 17% | [5 empty] | 1.5 | 6
Local Drainage | 5 | 22% |  | Speed Limit | Lane Width and Taper Length Needed
Street Modernization | 6 | 30% |  |  | 10' | 11' | 12'
Landscape Retrofit | 7 | 33% |  | 25 | 104 | 115 | 125
Screen Walls | 8 | 21% |  | 30 | 150 | 165 | 185
Sidewalks | 9 | 30% |  | 35 | 204 | 225 | 245
Bikeways | 10 | 20% |  | 40 | 267 | 293 | 320
Bottleneck Removal | 11 | 35% |  | 45 | 450 | 495 | 540
Pedestrian Bridges/Tunnels | 12 | 15% |  | 50 | 500 | 550 | 600
Traffic Calming | 13 | 45% |  | 55 | 550 | 605 | 660
Water Projects | 14 | 14%
Area of a Triangle
PIO Charges per project Type | Enter number into C153 |  |  | A = ab/2 | where ab meets at the 90 degree angle
Not Needed | 0 | 0
Local Drainage | 83 | 8500
Major Street | 85 | 12000
Sidewalks/St. Mods | 87 | 7000
Bridges | 89 | 8000
Major Street | 85 | 50000
Collector/Local St | 87 | 30000
12" Storm Drain Pipe | Lin. Ft. |  | 81 |  | CATCH BASIN PIPE (12") |  | Lin. Ft. | 60
15" Storm Drain Pipe | Lin. Ft. |  | 120 |  | CATCH BASIN PIPE (15") |  | Lin. Ft. | 90
18" Storm Drain Pipe | Lin. Ft. |  | 85 |  | CATCH BASIN PIPE (18") |  | Lin. Ft. | 90
24" Storm Drain Pipe | Lin. Ft. |  | 100 |  | CATCH BASIN PIPE (24") |  | Lin. Ft. | 130
30" Storm Drain Pipe | Lin. Ft. |  | 121 |  | CATCH BASIN PIPE (30") |  | Lin. Ft. | 150
36" Storm Drain Pipe | Lin. Ft. |  | 166
42" Storm Drain Pipe | Lin. Ft. |  | 190
48" Storm Drain Pipe | Lin. Ft. |  | 211
54" Storm Drain Pipe | Lin. Ft. |  | 305

## Proj_Schedule
35th Avenue Innovation Corridor Improvements, City of Phoenix
Project Schedule
This table provides the project schedule.
|  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024
| Project Task | Jan-March | April-June | July-Sept | Oct-Dec | Jan-March | April-June | July-Sep | Oct-Dec | Jan-March | April-June | July-Sept | Oct-Dec | Jan-March | April-June | July-Sept | Oct-Dec | Jan-March | April-June | July-Sept | Oct-Dec
Design | Prepare Preliminary DCR
Prepare Final DCR
Prepare 60% Plans
Prepare 95% Plans
Environmental | Conduct Environmental Surveys
Prepare Preliminary CatEx
Prepare Final CatEx
Utilities | Conduct Initial Utility Actions
Utility Clearance
ROW | Conduct Initial ROW Actions
ROW Acquisition
ROW Clearance
Approvals | Council Approval
Bid Package Approvals
Obligate Funds
Wait for Federal Authorization
Construction | Advertise for Construction
Mill and Overlay
Intersection Reconstruction
Center Median
Install HAWKs
Install Streelighting
Install Fiber
Install Progression Speed Signs

## O&M
Operations and Maintenance (O&M) Costs
Calculates the net O&M Costs between the Baseline and Build Option
Baseline O&M Costs for Project Area Per Year (without project implementation) | 313232 | in 2019$
Build O&M Costs for Project Area Per Year (with project implementation) | 398351 | in 2019$
Net O&M Costs | 85119 | in 2019$
Net O&M Costs | 81654.9426 | in 2017$
| 7% | Discount Rate
| 2019 | Discount Year
Year | Partial Year Operations | O&M Costs | Discounted O&M Costs (7%)
2020 | 0 | 0 | 0
2021 | 0 | 0 | 0
2022 | 0 | 0 | 0
2023 | 0 | 0 | 0
2024 | 0.25 | 20413.7356 | 14554.7114
2025 | 1 | 81654.9426 | 54410.136
2026 | 1 | 81654.9426 | 50850.5944
2027 | 1 | 81654.9426 | 47523.92
2028 | 1 | 81654.9426 | 44414.8785
2029 | 1 | 81654.9426 | 41509.2323
2030 | 1 | 81654.9426 | 38793.675
2031 | 1 | 81654.9426 | 36255.771
2032 | 1 | 81654.9426 | 33883.8982
2033 | 1 | 81654.9426 | 31667.1946
2034 | 1 | 81654.9426 | 29595.5089
2035 | 1 | 81654.9426 | 27659.3541
2036 | 1 | 81654.9426 | 25849.8637
2037 | 1 | 81654.9426 | 24158.7511
2038 | 1 | 81654.9426 | 22578.2721
2039 | 1 | 81654.9426 | 21101.1888
2040 | 1 | 81654.9426 | 19720.7372
2041 | 1 | 81654.9426 | 18430.5955
2042 | 1 | 81654.9426 | 17224.8557
2043 | 1 | 81654.9426 | 16097.9959
2044 | 0.75 | 61241.2069 | 11283.642
2045 | 0 | 0 | 0
Total |  | 1633098.852 | 627564.7766

## Safety
Roadway Safety Improvements
The project will strategically deploy concentrated safety countermeasures based on the needs and crash history along the corridor. The recommended mitigation strategies are research-proven methods to effectively reduce the severity and frequency of the types of crashes that have historically occurred along this corridor.
7% | Discount Rate
2019 | Discount Year
O – No Injury | 3200
C – Possible Injury | 63900
B – Non-incapacitating | 125000
A – Incapacitating | 459100
K – Killed | 9600000
U – Injured (Severity Unknown) | 174000
# Accidents Reported (Unknown if Injured) | 132200
Year | Fatalities | Incapacitating | Minor | Possible | PDO Avoided | Total Avoided | Fatalities Avoided- Savings | Incapacitating Injuries Avoided-Savings | Minor Injuries Avoided-Savings | Possible Injuries Avoided-Savings | PDO Avoided - Savings | Total Avoided-Savings | Discounted Safety Savings 7%
2020 | [12 empty] | 0
2021 | [12 empty] | 0
2022 | [12 empty] | 0
2023 | [12 empty] | 0
2024 | 0.054467 | 0.19064 | 0.699 | 1.2709 | 4.3325 | 6.5475 | 522885.2459 | 87520.6414 | 87374.4877 | 81210.6148 | 13864 | 792854.9898 | 565294.65
2025 | 0.21787 | 0.76254 | 2.796 | 5.0836 | 17.33 | 26.19 | 2091540.9836 | 350082.5656 | 349497.9508 | 324842.459 | 55456 | 3171419.959 | 2113251.0281
2026 | 0.21836 | 0.76426 | 2.8023 | 5.0951 | 17.37 | 26.25 | 2096262.2951 | 350872.8197 | 350286.8852 | 325575.7377 | 55584 | 3178581.7377 | 1979460.9567
2027 | 0.21885 | 0.76598 | 2.8086 | 5.1066 | 17.41 | 26.31 | 2100983.6066 | 351663.0738 | 351075.8197 | 326309.0164 | 55712 | 3185743.5164 | 1854131.7314
2028 | 0.21934 | 0.7677 | 2.8149 | 5.118 | 17.46 | 26.38 | 2105704.918 | 352453.3279 | 351864.7541 | 327042.2951 | 55872 | 3192937.2951 | 1736746.3328
2029 | 0.22008 | 0.77029 | 2.8244 | 5.1352 | 17.5 | 26.45 | 2112786.8852 | 353638.709 | 353048.1557 | 328142.2131 | 56000 | 3203615.9631 | 1628555.9071
2030 | 0.22057 | 0.77201 | 2.8307 | 5.1467 | 17.54 | 26.51 | 2117508.1967 | 354428.9631 | 353837.0902 | 328875.4918 | 56128 | 3210777.7418 | 1525417.3759
2031 | 0.22131 | 0.77459 | 2.8402 | 5.1639 | 17.59 | 26.59 | 2124590.1639 | 355614.3443 | 355020.4918 | 329975.4098 | 56288 | 3221488.4098 | 1430379.3805
2032 | 0.2218 | 0.77631 | 2.8465 | 5.1754 | 17.63 | 26.65 | 2129311.4754 | 356404.5984 | 355809.4262 | 330708.6885 | 56416 | 3228650.1885 | 1339775.0429
2033 | 0.22254 | 0.77889 | 2.8559 | 5.1926 | 17.68 | 26.73 | 2136393.4426 | 357589.9795 | 356992.8279 | 331808.6066 | 56576 | 3239360.8566 | 1256279.99
2034 | 0.22303 | 0.78061 | 2.8623 | 5.2041 | 17.72 | 26.79 | 2141114.7541 | 358380.2336 | 357781.7623 | 332541.8852 | 56704 | 3246522.6352 | 1176689.2068
2035 | 0.22377 | 0.7832 | 2.8717 | 5.2213 | 17.77 | 26.87 | 2148196.7213 | 359565.6148 | 358965.1639 | 333641.8033 | 56864 | 3257233.3033 | 1103337.6129
2036 | 0.22426 | 0.78492 | 2.878 | 5.2328 | 17.82 | 26.94 | 2152918.0328 | 360355.8689 | 359754.0984 | 334375.082 | 57024 | 3264427.082 | 1033434.0137
2037 | 0.225 | 0.7875 | 2.8875 | 5.25 | 17.86 | 27.01 | 2160000 | 361541.25 | 360937.5 | 335475 | 57152 | 3275105.75 | 968985.6136
2038 | 0.22549 | 0.78922 | 2.8938 | 5.2615 | 17.91 | 27.08 | 2164721.3115 | 362331.5041 | 361726.4344 | 336208.2787 | 57312 | 3282299.5287 | 907583.1711
2039 | 0.22623 | 0.7918 | 2.9033 | 5.2787 | 17.96 | 27.16 | 2171803.2787 | 363516.8852 | 362909.8361 | 337308.1967 | 57472 | 3293010.1967 | 850976.4113
2040 | 0.22672 | 0.79352 | 2.9096 | 5.2902 | 18.01 | 27.23 | 2176524.5902 | 364307.1393 | 363698.7705 | 338041.4754 | 57632 | 3300203.9754 | 797042.449
2041 | 0.22746 | 0.79611 | 2.9191 | 5.3074 | 18.05 | 27.3 | 2183606.5574 | 365492.5205 | 364882.1721 | 339141.3934 | 57760 | 3310882.6434 | 747309.801
2042 | 0.22795 | 0.79783 | 2.9254 | 5.3189 | 18.1 | 27.37 | 2188327.8689 | 366282.7746 | 365671.1066 | 339874.6721 | 57920 | 3318076.4221 | 699937.8799
2043 | 0.22869 | 0.80041 | 2.9348 | 5.3361 | 18.15 | 27.45 | 2195409.8361 | 367468.1557 | 366854.5082 | 340974.5902 | 58080 | 3328787.0902 | 656259.1234
2044 | 0.17207 | 0.60224 | 2.2082 | 4.015 | 13.65 | 20.6475 | 1651868.8525 | 276490.1527 | 276028.4324 | 256555.8811 | 43680 | 2504623.3186 | 461474.7865
2045 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [6 empty] | 42872459.0164 |  |  |  | 1135496 | 65006602.6035 | 24832322.4647

## CrashReduction
Crash Reduction Calculation
This sheet calculates the reduction in crashes involving fatalities/injuries based on historical distributions by KABCO category to be used in the safety benefits analysis.
Summary table of results from Safety Modeling for the Project
2019 Predictive Safety Analysis
Crash reduction distributed based on historical proportions of fatal/injury crash category in the project corridor
|  | Crash Reduction by Year |  |  | Crash Reduction by Year
|  | Fatal/Injury | PDO | Total Crashes | Year | Total Fatal/Injury | Fatal | Incapacitating | Minor | Possible
| 2024 | 8.86 | 17.33 | 26.19 | 2024 | 8.86 | 0.21787 | 0.76254 | 2.796 | 5.0836
| 2025 | 8.86 | 17.33 | 26.19 | 2025 | 8.86 | 0.21787 | 0.76254 | 2.796 | 5.0836
| 2026 | 8.88 | 17.37 | 26.25 | 2026 | 8.88 | 0.21836 | 0.76426 | 2.8023 | 5.0951
| 2027 | 8.9 | 17.41 | 26.31 | 2027 | 8.9 | 0.21885 | 0.76598 | 2.8086 | 5.1066
| 2028 | 8.92 | 17.46 | 26.38 | 2028 | 8.92 | 0.21934 | 0.7677 | 2.8149 | 5.118
| 2029 | 8.95 | 17.5 | 26.45 | 2029 | 8.95 | 0.22008 | 0.77029 | 2.8244 | 5.1352
| 2030 | 8.97 | 17.54 | 26.52 | 2030 | 8.97 | 0.22057 | 0.77201 | 2.8307 | 5.1467
| 2031 | 9 | 17.59 | 26.59 | 2031 | 9 | 0.22131 | 0.77459 | 2.8402 | 5.1639
| 2032 | 9.02 | 17.63 | 26.66 | 2032 | 9.02 | 0.2218 | 0.77631 | 2.8465 | 5.1754
| 2033 | 9.05 | 17.68 | 26.72 | 2033 | 9.05 | 0.22254 | 0.77889 | 2.8559 | 5.1926
| 2034 | 9.07 | 17.72 | 26.79 | 2034 | 9.07 | 0.22303 | 0.78061 | 2.8623 | 5.2041
| 2035 | 9.1 | 17.77 | 26.87 | 2035 | 9.1 | 0.22377 | 0.7832 | 2.8717 | 5.2213
| 2036 | 9.12 | 17.82 | 26.94 | 2036 | 9.12 | 0.22426 | 0.78492 | 2.878 | 5.2328
| 2037 | 9.15 | 17.86 | 27.01 | 2037 | 9.15 | 0.225 | 0.7875 | 2.8875 | 5.25
| 2038 | 9.17 | 17.91 | 27.08 | 2038 | 9.17 | 0.22549 | 0.78922 | 2.8938 | 5.2615
| 2039 | 9.2 | 17.96 | 27.16 | 2039 | 9.2 | 0.22623 | 0.7918 | 2.9033 | 5.2787
| 2040 | 9.22 | 18.01 | 27.23 | 2040 | 9.22 | 0.22672 | 0.79352 | 2.9096 | 5.2902
| 2041 | 9.25 | 18.05 | 27.3 | 2041 | 9.25 | 0.22746 | 0.79611 | 2.9191 | 5.3074
| 2042 | 9.27 | 18.1 | 27.38 | 2042 | 9.27 | 0.22795 | 0.79783 | 2.9254 | 5.3189
| 2043 | 9.3 | 18.15 | 27.45 | 2043 | 9.3 | 0.22869 | 0.80041 | 2.9348 | 5.3361
| 2044 | 9.33 | 18.2 | 27.52 | 2044 | 9.33 | 0.22943 | 0.80299 | 2.9443 | 5.3533
| Total | 181.73 | 355.07 | 536.8
Historical proportions of fatal/injury crash category in the project corridor (based on recent 5 year data)
[7 empty] | Fatal | Incapacitating | Minor | Possible | Total
[6 empty] | Annual Crashes | 2.4 | 8.4 | 30.8 | 56 | 97.6
[6 empty] | Proportion | 0.02459 | 0.086066 | 0.31557 | 0.57377 | 1
[6 empty] | 2034 Estimate | 0.22303 | 0.78061 | 2.8623 | 5.2041 | 9.07

## Residual
Residual Value
Project components will have a useful life longer than the analysis period
Type of asset | Service life (years)
Telecommunications/20/ | 40
Highways and streets | 60
Conservation and development | 60
Sewer systems | 60
Water systems | 60
Miscellaneous electrical machinery | 12
Other | 60
Other Furniture | 14
Other electrical equipment | 9
Electric Light and Power (1946 and later years) | 45
Local Transit | 38
Source: BEA Rate of Depreciation, Service Lives, Declining-Balance Rates, and Hulten-Wykoff Categories
http://www.bea.gov/scb/account_articles/national/wlth2594/tableC.htm
Discount Rate | 7%
Discount Year | 2019
End of Analysis Period | 2044
Project Start Year | 2024
Analysis Period | 20
| Useful Life (Years) | % of Construction Cost | 2019$ | 2017 $ | % of Useful Life Remaining at End of Analysis Period | Remaining Value in 2044 ($2017) | Discounted at 7%
ROW (Does not Depreciate) |  |  | 1993280 | 1912160.199 | 100% | 1912160.199 | 352313.944
Streetlights, electrical and powerline related | 45 | n/a | 3709200 | 3559367.8871 | 55.56% | 1977426.604 | 364339.2254
Roadway/street related (medians) | 60 | n/a | 600000 | 575763.1652 | 66.67% | 383842.1101 | 70722.5931
Signals, fiber, ITS related | 40 | n/a | 4000000 | 3838421.1012 | 50% | 1919210.5506 | 353612.9654
n/a
|  |  |  | 9885712.3525 |  | 6192639.4637 | 1140988.7279

## TravelTimeSavings
Travel Time Savings
By optimizing signal timing and enabling future ITS applications that can assist with traffic management, the project will allow people to move through the corridor more efficiently. As a result, the project has a direct economic benefit to the community from travel time savings
| 7% | Discount Rate
| 2019 | Discount Year
| 260 | Annualization factor
| 1.32 | vehicle occupancy rate
| 14.8 | Value of time, all purpose
since this is arterial network, analysis conservatively assumes most of the traffic would be auto/cars
|  | Year | Annual VHT Saved | Partial Year Operations | Annual VHT Saved - Op Years | Annual Person Hours Saved | Total Travel Time Savings Value (Not Discounted) | Total Travel Time Savings Value (Discounted at 7%)
|  | 2020 |  | 0
|  | 2021 |  | 0
|  | 2022 |  | 0
|  | 2023 |  | 0
| assumed the same as 2025 | 2024 | 94296.6538 | 0.25 | 23574.1635 | 31117.8958 | 460544.8573 | 328362.1183 | 328362.1183
|  | 2025 | 94296.6538 | 1 | 94296.6538 | 124471.583 | 1842179.4291 | 1227521.9375 | 1227521.9375
|  | 2026 | 94194.3279 | 1 | 94194.3279 | 124336.5128 | 1840180.3901 | 1145971.863 | 1145971.863
|  | 2027 | 94092.113 | 1 | 94092.113 | 124201.5892 | 1838183.5204 | 1069839.5448 | 1069839.5448
|  | 2028 | 93990.0091 | 1 | 93990.0091 | 124066.812 | 1836188.8176 | 998765.0557 | 998765.0557
|  | 2029 | 93888.0159 | 1 | 93888.0159 | 123932.181 | 1834196.2794 | 932412.3803 | 932412.3803
|  | 2030 | 93786.1335 | 1 | 93786.1335 | 123797.6962 | 1832205.9033 | 870467.8262 | 870467.8262
|  | 2031 | 93684.3615 | 1 | 93684.3615 | 123663.3572 | 1830217.6871 | 812638.5411 | 812638.5411
|  | 2032 | 93582.7001 | 1 | 93582.7001 | 123529.1641 | 1828231.6284 | 758651.1283 | 758651.1283
|  | 2033 | 93481.1489 | 1 | 93481.1489 | 123395.1165 | 1826247.7249 | 708250.3541 | 708250.3541
|  | 2034 | 93379.7079 | 1 | 93379.7079 | 123261.2145 | 1824265.9742 | 661197.9411 | 661197.9411
|  | 2035 | 93278.377 | 1 | 93278.377 | 123127.4577 | 1822286.374 | 617271.442 | 617271.442
|  | 2036 | 93177.1561 | 1 | 93177.1561 | 122993.8461 | 1820308.922 | 576263.1874 | 576263.1874
|  | 2037 | 93076.045 | 1 | 93076.045 | 122860.3794 | 1818333.6157 | 537979.3047 | 537979.3047
|  | 2038 | 92975.0437 | 1 | 92975.0437 | 122727.0576 | 1816360.453 | 502238.801 | 502238.801
|  | 2039 | 92874.1519 | 1 | 92874.1519 | 122593.8805 | 1814389.4315 | 468872.7076 | 468872.7076
|  | 2040 | 92773.3696 | 1 | 92773.3696 | 122460.8479 | 1812420.5488 | 437723.2812 | 437723.2812
|  | 2041 | 92082.5645 | 1 | 92082.5645 | 121548.9851 | 1798924.9797 | 406041.0511 | 406041.0511
|  | 2042 | 91396.9032 | 1 | 91396.9032 | 120643.9122 | 1785529.9008 | 376651.9677 | 376651.9677
|  | 2043 | 90716.3474 | 1 | 90716.3474 | 119745.5786 | 1772234.5637 | 349390.054 | 349390.054
|  | 2044 | 90040.8592 | 0.75 | 67530.6444 | 89140.4506 | 1319278.6693 | 243076.0097 | 243076.0097
|  | 2045 | 89370.4008 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  |  |  |  | 36372709.6704 | 14029586.4966 | 14029586.4966

## Emissions
Idling Emissions Savings
By optimizing signal timing and enabling future ITS applications that can assist with traffic management, the project will allow people to move through the corridor more efficiently and resulting in reduced idling emissions
| Discount Rate | 7%
| Discount Year | 2019
| Short tons per Metric Ton | 1.1015
| Grams per Short Ton | 907185
| Grams per Metric Ton | 1000000
| LDGV Emissions Rates g/hr VOC | 3.0997
| LDGV Emissions Rates g/hr N2O | 3.6715
| LDGV Emissions Rates g/hr CO2 | 2443.925
| LDGV Emissions Rates g/hr PM2.5 | 0.024293
| VOC Value of Emissions (2017$) per short ton | 2000
| N2O Value of Emissions (2017$) per short ton | 8300
| CO2 Value of Emissions (2017$) per metric ton | Varies
| PM2.5 Value of Emissions (2017$) per short ton | 377800
Year | Vehicle Delay Hours Avoided | VOC Short Tons Avoided | N2O Short Tons Avoided | CO2 Metric Tons Avoided | PM2.5 Short Tons Avoided | VOC Emissions Savings | N2O Emissions Savings | CO2 Emissions Savings | PM2.5 Emissions Savings | Social Cost of CO2 Per Metric Ton | Emission Savings | Discounted at 7%
2020
2021
2022
2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
2024 | 23574.1635 | 0.080549 | 0.095408 | 57.6135 | 0.00063127 | 161.098 | 791.8849 | 57.6135 | 238.4941 | 1 | 1249.0905 | 890.5843
2025 | 94296.6538 | 0.3222 | 0.38163 | 230.4539 | 0.0025251 | 644.3919 | 3167.5395 | 230.4539 | 953.9766 | 1 | 4996.362 | 3329.287
2026 | 94194.3279 | 0.32185 | 0.38122 | 230.2039 | 0.0025223 | 643.6926 | 3164.1023 | 230.2039 | 952.9414 | 1 | 4990.9402 | 3108.1067
2027 | 94092.113 | 0.3215 | 0.3808 | 229.9541 | 0.0025196 | 642.9941 | 3160.6688 | 229.9541 | 951.9073 | 1 | 4985.5243 | 2901.6205
2028 | 93990.0091 | 0.32115 | 0.38039 | 229.7045 | 0.0025169 | 642.2964 | 3157.239 | 229.7045 | 950.8743 | 1 | 4980.1142 | 2708.8522
2029 | 93888.0159 | 0.3208 | 0.37998 | 229.4553 | 0.0025141 | 641.5994 | 3153.8129 | 229.4553 | 949.8425 | 1 | 4974.7101 | 2528.8903
2030 | 93786.1335 | 0.32045 | 0.37957 | 229.2063 | 0.0025114 | 640.9032 | 3150.3905 | 229.2063 | 948.8118 | 1 | 4969.3118 | 2360.8842
2031 | 93684.3615 | 0.3201 | 0.37915 | 228.9576 | 0.0025087 | 640.2077 | 3146.9719 | 228.9576 | 947.7822 | 1 | 4963.9193 | 2204.0396
2032 | 93582.7001 | 0.31976 | 0.37874 | 228.7091 | 0.002506 | 639.513 | 3143.557 | 228.7091 | 946.7537 | 1 | 4958.5327 | 2057.6148
2033 | 93481.1489 | 0.31941 | 0.37833 | 228.4609 | 0.0025032 | 638.819 | 3140.1457 | 228.4609 | 945.7263 | 1 | 4953.152 | 1920.9177
2034 | 93379.7079 | 0.31906 | 0.37792 | 228.213 | 0.0025005 | 638.1258 | 3136.7382 | 228.213 | 944.7001 | 1 | 4947.7771 | 1793.3021
2035 | 93278.377 | 0.31872 | 0.37751 | 227.9654 | 0.0024978 | 637.4333 | 3133.3344 | 455.9307 | 943.6749 | 2 | 5170.3734 | 1751.3843
2036 | 93177.1561 | 0.31837 | 0.3771 | 227.718 | 0.0024951 | 636.7416 | 3129.9343 | 455.436 | 942.6509 | 2 | 5164.7627 | 1635.0316
2037 | 93076.045 | 0.31803 | 0.37669 | 227.4709 | 0.0024924 | 636.0507 | 3126.5378 | 454.9417 | 941.628 | 2 | 5159.1582 | 1526.4088
2038 | 92975.0437 | 0.31768 | 0.37628 | 227.224 | 0.0024897 | 635.3605 | 3123.1451 | 454.4481 | 940.6062 | 2 | 5153.5598 | 1425.0022
2039 | 92874.1519 | 0.31734 | 0.37587 | 226.9775 | 0.002487 | 634.671 | 3119.756 | 453.9549 | 939.5855 | 2 | 5147.9674 | 1330.3326
2040 | 92773.3696 | 0.31699 | 0.37547 | 226.7312 | 0.0024843 | 633.9823 | 3116.3706 | 453.4623 | 938.5659 | 2 | 5142.3811 | 1241.9523
2041 | 92082.5645 | 0.31463 | 0.37267 | 225.0429 | 0.0024658 | 629.2616 | 3093.1656 | 450.0858 | 931.5772 | 2 | 5104.0901 | 1152.0603
2042 | 91396.9032 | 0.31229 | 0.3699 | 223.3672 | 0.0024474 | 624.576 | 3070.1334 | 446.7344 | 924.6405 | 2 | 5066.0842 | 1068.6747
2043 | 90716.3474 | 0.30996 | 0.36714 | 221.7039 | 0.0024292 | 619.9253 | 3047.2727 | 443.4079 | 917.7555 | 2 | 5028.3614 | 991.3244
2044 | 67530.6444 | 0.23074 | 0.27331 | 165.0398 | 0.0018083 | 461.4819 | 2268.4367 | 330.0797 | 683.1913 | 2 | 3743.1895 | 689.6796
2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Total | [11 empty] | 38615.9503

## Deflator
Table 10.1 - GROSS DOMESTIC PRODUCT AND DEFLATORS USED IN THE HISTORICAL TABLES: 1940 - 2024
(Fiscal Year 2012 = 1.000)
Fiscal Year | GDP (in billions of dollars) | GDP (Chained) Price Index | Composite Outlay Deflators
|  |  | Total | Total Defense | Total Nondefense | Payment for Individuals |  |  | Other Grants | Net Interest | Undis- tributed Offsetting Receipts | All Other | Addendum: Direct Capital
[6 empty] | Total | Direct | Grants |  |  |  |  | Total | Defense | Nondefense
1940 | 98.2 | 0.0771 | 0.0653 | 0.0614 | 0.0662 | 0.0741 | 0.0741 | 0.0741 | 0.0463 | 0.0771 | 0.0442 | 0.0627 | 0.1378 | 0.143 | 0.1357
1941 | 116.2 | 0.08 | 0.0724 | 0.0756 | 0.0697 | 0.0767 | 0.0767 | 0.0767 | 0.0419 | 0.08 | 0.0439 | 0.0641 | 0.1487 | 0.1516 | 0.1421
1942 | 147.7 | 0.086 | 0.0823 | 0.0925 | 0.0633 | 0.0839 | 0.0839 | 0.0839 | 0.0411 | 0.086 | 0.0471 | 0.0553 | 0.1555 | 0.1557 | 0.1533
1943 | 184.6 | 0.0915 | 0.0912 | 0.0993 | 0.0625 | 0.0929 | 0.0929 | 0.0929 | 0.0438 | 0.0915 | 0.0516 | 0.0542 | 0.1525 | 0.1525 | 0.1562
1944 | 213.8 | 0.0948 | 0.0837 | 0.0869 | 0.0676 | 0.0998 | 0.0998 | 0.0998 | 0.0461 | 0.0948 | 0.0568 | 0.0578 | 0.1481 | 0.148 | 0.1633
1945 | 226.4 | 0.0971 | 0.0789 | 0.079 | 0.0778 | 0.105 | 0.105 | 0.1047 | 0.0466 | 0.0971 | 0.0599 | 0.0614 | 0.1381 | 0.138 | 0.169
1946 | 228 | 0.1045 | 0.0793 | 0.0754 | 0.0958 | 0.1106 | 0.1106 | 0.1104 | 0.0514 | 0.1045 | 0.0623 | 0.0667 | 0.1402 | 0.1398 | 0.1596
1947 | 238.9 | 0.1159 | 0.0897 | 0.0813 | 0.0955 | 0.1189 | 0.1189 | 0.1188 | 0.1246 | 0.1159 | 0.0661 | 0.0688 | 0.1561 | 0.1557 | 0.1581
1948 | 261.9 | 0.1269 | 0.0932 | 0.0763 | 0.1034 | 0.1299 | 0.1299 | 0.1298 | 0.07 | 0.1269 | 0.0714 | 0.0757 | 0.1736 | 0.1708 | 0.184
1949 | 276.5 | 0.1312 | 0.0896 | 0.0759 | 0.0988 | 0.1333 | 0.1333 | 0.1332 | 0.0737 | 0.1312 | 0.0694 | 0.0737 | 0.1823 | 0.18 | 0.1877
1950 | 278.675 | 0.1294 | 0.0942 | 0.0767 | 0.1056 | 0.1316 | 0.1317 | 0.1312 | 0.0699 | 0.1294 | 0.0731 | 0.0788 | 0.1804 | 0.1793 | 0.1821
1951 | 327.05 | 0.1363 | 0.0947 | 0.0813 | 0.1151 | 0.139 | 0.1391 | 0.1385 | 0.0836 | 0.1363 | 0.0721 | 0.0805 | 0.1924 | 0.193 | 0.1898
1952 | 357.1 | 0.1418 | 0.0944 | 0.0845 | 0.1259 | 0.1446 | 0.1446 | 0.1441 | 0.0839 | 0.1418 | 0.0776 | 0.0877 | 0.2019 | 0.2018 | 0.2025
1953 | 382.05 | 0.1444 | 0.1015 | 0.0933 | 0.1268 | 0.1467 | 0.1468 | 0.1463 | 0.0879 | 0.1444 | 0.0821 | 0.0922 | 0.2045 | 0.2042 | 0.2089
1954 | 387.15 | 0.1461 | 0.1047 | 0.0949 | 0.1366 | 0.1486 | 0.1486 | 0.1484 | 0.0842 | 0.1461 | 0.085 | 0.0987 | 0.2026 | 0.2023 | 0.2073
1955 | 406.325 | 0.1472 | 0.1081 | 0.098 | 0.1306 | 0.1485 | 0.1485 | 0.1484 | 0.0858 | 0.1472 | 0.0873 | 0.0954 | 0.2083 | 0.2086 | 0.2033
1956 | 438.25 | 0.151 | 0.113 | 0.1039 | 0.1302 | 0.1503 | 0.1503 | 0.1502 | 0.0871 | 0.151 | 0.0883 | 0.0951 | 0.2193 | 0.2198 | 0.2107
1957 | 463.375 | 0.1566 | 0.1186 | 0.1093 | 0.1353 | 0.1545 | 0.1545 | 0.1544 | 0.095 | 0.1566 | 0.0904 | 0.0984 | 0.2315 | 0.2322 | 0.2212
1958 | 473.475 | 0.1613 | 0.1256 | 0.1144 | 0.1441 | 0.1591 | 0.1591 | 0.159 | 0.1053 | 0.1613 | 0.0967 | 0.1069 | 0.2388 | 0.2397 | 0.228
1959 | 504.6 | 0.1638 | 0.1308 | 0.1223 | 0.142 | 0.1613 | 0.1613 | 0.1612 | 0.1126 | 0.1638 | 0.1015 | 0.1106 | 0.243 | 0.244 | 0.2317
1960 | 534.325 | 0.1661 | 0.1328 | 0.121 | 0.1486 | 0.1643 | 0.1644 | 0.1642 | 0.1132 | 0.1661 | 0.1007 | 0.1143 | 0.2447 | 0.2459 | 0.2348
1961 | 546.575 | 0.1683 | 0.1358 | 0.1233 | 0.1516 | 0.1666 | 0.1666 | 0.1665 | 0.1111 | 0.1683 | 0.1057 | 0.1205 | 0.2461 | 0.2473 | 0.2366
1962 | 585.675 | 0.17 | 0.1359 | 0.1234 | 0.1505 | 0.1682 | 0.1682 | 0.1681 | 0.1115 | 0.17 | 0.1078 | 0.1224 | 0.2481 | 0.2494 | 0.2387
1963 | 618.2 | 0.172 | 0.1418 | 0.129 | 0.1562 | 0.1702 | 0.1702 | 0.1701 | 0.1155 | 0.172 | 0.1113 | 0.1302 | 0.2521 | 0.2536 | 0.241
1964 | 661.7 | 0.1742 | 0.1441 | 0.1307 | 0.158 | 0.1726 | 0.1726 | 0.1725 | 0.1175 | 0.1742 | 0.1149 | 0.1366 | 0.2525 | 0.2538 | 0.2446
1965 | 709.325 | 0.1772 | 0.1461 | 0.1303 | 0.1606 | 0.1749 | 0.175 | 0.1748 | 0.1207 | 0.1772 | 0.1214 | 0.1423 | 0.2531 | 0.2545 | 0.2468
1966 | 780.475 | 0.181 | 0.1501 | 0.1365 | 0.1624 | 0.1781 | 0.1781 | 0.178 | 0.1174 | 0.181 | 0.1255 | 0.1464 | 0.2552 | 0.2566 | 0.2482
1967 | 836.525 | 0.1865 | 0.1534 | 0.1409 | 0.1656 | 0.1829 | 0.1829 | 0.1828 | 0.1189 | 0.1865 | 0.1287 | 0.1484 | 0.259 | 0.26 | 0.252
1968 | 897.575 | 0.193 | 0.159 | 0.1476 | 0.1703 | 0.1886 | 0.1886 | 0.1885 | 0.1231 | 0.193 | 0.1334 | 0.1516 | 0.2647 | 0.2655 | 0.2577
1969 | 980.275 | 0.2018 | 0.1691 | 0.156 | 0.1816 | 0.1966 | 0.1966 | 0.1965 | 0.1305 | 0.2018 | 0.1427 | 0.1632 | 0.2748 | 0.2755 | 0.2677
1970 | 1046.675 | 0.2126 | 0.1785 | 0.164 | 0.1907 | 0.2059 | 0.2059 | 0.2058 | 0.1393 | 0.2126 | 0.1545 | 0.1733 | 0.289 | 0.2897 | 0.2826
1971 | 1116.55 | 0.2234 | 0.1909 | 0.1742 | 0.2025 | 0.2151 | 0.2151 | 0.215 | 0.1491 | 0.2234 | 0.1701 | 0.1897 | 0.3069 | 0.3079 | 0.3002
1972 | 1216.25 | 0.234 | 0.2033 | 0.1908 | 0.2105 | 0.2233 | 0.2233 | 0.2232 | 0.1561 | 0.234 | 0.1832 | 0.2021 | 0.3302 | 0.3333 | 0.3147
1973 | 1352.725 | 0.2442 | 0.2126 | 0.2042 | 0.2166 | 0.2317 | 0.2317 | 0.2316 | 0.1594 | 0.2442 | 0.1938 | 0.2138 | 0.3515 | 0.3569 | 0.328
1974 | 1482.85 | 0.2616 | 0.2304 | 0.2181 | 0.236 | 0.2504 | 0.2504 | 0.2503 | 0.1744 | 0.2616 | 0.2057 | 0.2261 | 0.3725 | 0.3771 | 0.3533
1975 | 1606.925 | 0.2886 | 0.2528 | 0.2376 | 0.2586 | 0.2762 | 0.2762 | 0.2761 | 0.1934 | 0.2886 | 0.2211 | 0.241 | 0.4049 | 0.4083 | 0.3924
1976 | 1786.1 | 0.3087 | 0.2709 | 0.2525 | 0.2773 | 0.2942 | 0.2942 | 0.2941 | 0.2086 | 0.3087 | 0.2395 | 0.2624 | 0.4302 | 0.4342 | 0.4162
TQ | 471.65 | 0.318 | 0.2776 | 0.2574 | 0.2844 | 0.3034 | 0.3034 | 0.3033 | 0.2163 | 0.318 | 0.2467 | 0.2681 | 0.4442 | 0.4497 | 0.4274
1977 | 2024.325 | 0.331 | 0.2906 | 0.2725 | 0.2968 | 0.3163 | 0.3164 | 0.3162 | 0.2237 | 0.331 | 0.2582 | 0.2818 | 0.4632 | 0.4696 | 0.4409
1978 | 2273.45 | 0.3533 | 0.3088 | 0.2911 | 0.3144 | 0.3375 | 0.3376 | 0.3374 | 0.2379 | 0.3533 | 0.2746 | 0.2976 | 0.4918 | 0.5007 | 0.4634
1979 | 2565.575 | 0.3818 | 0.3356 | 0.3149 | 0.3424 | 0.3655 | 0.3656 | 0.3654 | 0.2597 | 0.3818 | 0.2922 | 0.3209 | 0.5257 | 0.535 | 0.4944
1980 | 2791.9 | 0.4151 | 0.3711 | 0.3485 | 0.3783 | 0.4042 | 0.4043 | 0.4041 | 0.2889 | 0.4151 | 0.3172 | 0.3443 | 0.5652 | 0.5721 | 0.5392
1981 | 3133.225 | 0.4559 | 0.4122 | 0.3865 | 0.4206 | 0.4436 | 0.4436 | 0.4434 | 0.323 | 0.4559 | 0.346 | 0.3753 | 0.6155 | 0.6223 | 0.5871
1982 | 3313.35 | 0.4876 | 0.4439 | 0.421 | 0.452 | 0.4711 | 0.4711 | 0.4709 | 0.352 | 0.4876 | 0.3637 | 0.3942 | 0.6637 | 0.6703 | 0.6292
1983 | 3536 | 0.5089 | 0.4657 | 0.4417 | 0.4747 | 0.4926 | 0.4926 | 0.4924 | 0.3702 | 0.5089 | 0.3757 | 0.4054 | 0.7028 | 0.7106 | 0.651
1984 | 3949.175 | 0.5271 | 0.488 | 0.4646 | 0.4971 | 0.5115 | 0.5115 | 0.5113 | 0.3895 | 0.5271 | 0.3858 | 0.4282 | 0.7314 | 0.7415 | 0.6689
1985 | 4265.125 | 0.5447 | 0.5059 | 0.4827 | 0.515 | 0.5294 | 0.5294 | 0.5291 | 0.406 | 0.5447 | 0.4023 | 0.4465 | 0.7382 | 0.7474 | 0.6838
1986 | 4526.25 | 0.5569 | 0.5165 | 0.4935 | 0.5258 | 0.5432 | 0.5432 | 0.5429 | 0.4206 | 0.5569 | 0.4072 | 0.4464 | 0.733 | 0.7389 | 0.6921
1987 | 4767.65 | 0.5694 | 0.5314 | 0.5008 | 0.5444 | 0.5571 | 0.5572 | 0.5569 | 0.4421 | 0.5694 | 0.4088 | 0.456 | 0.7258 | 0.7295 | 0.7016
1988 | 5138.55 | 0.5878 | 0.5497 | 0.5134 | 0.5646 | 0.5783 | 0.5784 | 0.5779 | 0.459 | 0.5878 | 0.4217 | 0.4737 | 0.7272 | 0.7282 | 0.7216
1989 | 5554.675 | 0.6116 | 0.5714 | 0.5332 | 0.5866 | 0.604 | 0.6041 | 0.6031 | 0.4782 | 0.6116 | 0.4324 | 0.4818 | 0.7437 | 0.7434 | 0.7455
1990 | 5898.75 | 0.634 | 0.588 | 0.5515 | 0.6004 | 0.6286 | 0.6288 | 0.6273 | 0.5014 | 0.634 | 0.4442 | 0.4834 | 0.757 | 0.7557 | 0.7646
1991 | 6093.175 | 0.6566 | 0.6143 | 0.5788 | 0.6243 | 0.6536 | 0.6538 | 0.652 | 0.5224 | 0.6566 | 0.4709 | 0.5084 | 0.7749 | 0.7732 | 0.7842
1992 | 6416.25 | 0.673 | 0.6393 | 0.588 | 0.655 | 0.6707 | 0.671 | 0.6689 | 0.5378 | 0.673 | 0.4876 | 0.5532 | 0.7868 | 0.7859 | 0.7907
1993 | 6775.325 | 0.6888 | 0.6582 | 0.5939 | 0.6773 | 0.6879 | 0.6884 | 0.6856 | 0.5546 | 0.6888 | 0.513 | 0.596 | 0.8057 | 0.8063 | 0.8035
1994 | 7176.85 | 0.7038 | 0.6698 | 0.5995 | 0.6891 | 0.7023 | 0.7029 | 0.6992 | 0.5689 | 0.7038 | 0.5361 | 0.6024 | 0.825 | 0.827 | 0.8174
1995 | 7560.425 | 0.7188 | 0.6897 | 0.6111 | 0.7097 | 0.7174 | 0.7181 | 0.7143 | 0.5884 | 0.7188 | 0.5531 | 0.6429 | 0.846 | 0.8479 | 0.8404
1996 | 7951.325 | 0.7323 | 0.7042 | 0.6243 | 0.7232 | 0.732 | 0.7326 | 0.7288 | 0.6056 | 0.7323 | 0.5794 | 0.6622 | 0.8567 | 0.8603 | 0.8472
1997 | 8451.025 | 0.7453 | 0.719 | 0.634 | 0.7392 | 0.7468 | 0.7474 | 0.7435 | 0.6173 | 0.7453 | 0.5937 | 0.6771 | 0.855 | 0.8572 | 0.8492
1998 | 8930.8 | 0.7546 | 0.725 | 0.646 | 0.7426 | 0.7538 | 0.7543 | 0.7515 | 0.6251 | 0.7546 | 0.606 | 0.6629 | 0.8557 | 0.8572 | 0.8505
1999 | 9479.35 | 0.7643 | 0.7339 | 0.6589 | 0.7504 | 0.7628 | 0.7632 | 0.7608 | 0.6403 | 0.7643 | 0.6245 | 0.6818 | 0.8643 | 0.8675 | 0.8562
2000 | 10117.45 | 0.78 | 0.7525 | 0.6821 | 0.7681 | 0.7807 | 0.7812 | 0.7784 | 0.6646 | 0.78 | 0.6568 | 0.7077 | 0.8765 | 0.8782 | 0.8728
2001 | 10526.5 | 0.7984 | 0.7722 | 0.7054 | 0.7867 | 0.7981 | 0.7985 | 0.796 | 0.6859 | 0.7984 | 0.6714 | 0.7302 | 0.8807 | 0.88 | 0.8821
2002 | 10833.65 | 0.8112 | 0.7841 | 0.7284 | 0.7969 | 0.8073 | 0.8078 | 0.8054 | 0.6996 | 0.8112 | 0.7092 | 0.7562 | 0.8762 | 0.8739 | 0.8814
2003 | 11283.8 | 0.826 | 0.8064 | 0.7755 | 0.8139 | 0.8232 | 0.8237 | 0.8213 | 0.7195 | 0.826 | 0.7476 | 0.7885 | 0.8831 | 0.8822 | 0.8854
2004 | 12025.45 | 0.8458 | 0.8274 | 0.8047 | 0.8332 | 0.8415 | 0.8419 | 0.8399 | 0.7463 | 0.8458 | 0.7837 | 0.8146 | 0.895 | 0.8943 | 0.8971
2005 | 12834.15 | 0.8716 | 0.8558 | 0.8431 | 0.8591 | 0.8652 | 0.8654 | 0.864 | 0.79 | 0.8716 | 0.8203 | 0.8437 | 0.9117 | 0.9108 | 0.9147
2006 | 13638.375 | 0.8995 | 0.8854 | 0.8792 | 0.887 | 0.8915 | 0.8916 | 0.8906 | 0.8306 | 0.8995 | 0.8504 | 0.8711 | 0.9266 | 0.9264 | 0.9274
2007 | 14290.8 | 0.924 | 0.9099 | 0.9081 | 0.9103 | 0.9109 | 0.9109 | 0.9105 | 0.8755 | 0.924 | 0.8812 | 0.9033 | 0.9396 | 0.9401 | 0.9381
2008 | 14743.325 | 0.9431 | 0.9414 | 0.9431 | 0.9409 | 0.9428 | 0.9428 | 0.9426 | 0.9188 | 0.9431 | 0.9097 | 0.9255 | 0.9569 | 0.9571 | 0.956
2009 | 14431.8 | 0.954 | 0.9413 | 0.9412 | 0.9414 | 0.942 | 0.942 | 0.9421 | 0.9323 | 0.954 | 0.9284 | 0.9343 | 0.9643 | 0.9655 | 0.9608
2010 | 14838.85 | 0.9622 | 0.9581 | 0.9583 | 0.9581 | 0.9583 | 0.9583 | 0.9581 | 0.9473 | 0.9622 | 0.9551 | 0.9633 | 0.9698 | 0.9697 | 0.9703
2011 | 15403.675 | 0.9814 | 0.9805 | 0.9864 | 0.9791 | 0.9791 | 0.9791 | 0.9789 | 0.974 | 0.9814 | 0.9888 | 0.9869 | 0.9895 | 0.9887 | 0.9917
2012 | 16056.45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2013 | 16603.775 | 1.0184 | 1.0142 | 1.007 | 1.0159 | 1.0148 | 1.0148 | 1.0148 | 1.0264 | 1.0184 | 1.0082 | 1.0126 | 1.004 | 1.0031 | 1.0065
2014 | 17332.9 | 1.0381 | 1.0302 | 1.0229 | 1.0317 | 1.0303 | 1.0303 | 1.0304 | 1.0509 | 1.0381 | 1.0432 | 1.0327 | 1.017 | 1.0152 | 1.0225
2015 | 18090.325 | 1.0507 | 1.0358 | 1.0271 | 1.0375 | 1.0351 | 1.0351 | 1.0353 | 1.061 | 1.0507 | 1.0595 | 1.0504 | 1.0198 | 1.0169 | 1.0278
2016 | 18550.95 | 1.0604 | 1.043 | 1.0305 | 1.0453 | 1.0429 | 1.0429 | 1.043 | 1.0652 | 1.0604 | 1.072 | 1.0593 | 1.0165 | 1.0131 | 1.0266
2017 | 19272.25 | 1.0796 | 1.0607 | 1.0458 | 1.0634 | 1.0607 | 1.0607 | 1.0608 | 1.0873 | 1.0796 | 1.1022 | 1.0815 | 1.0239 | 1.0192 | 1.0405
2018 | 20235.9 | 1.103 | 1.0872 | 1.068 | 1.0908 | 1.0875 | 1.0874 | 1.0877 | 1.1257 | 1.103 | 1.1261 | 1.1081 | 1.0454 | 1.0413 | 1.0628
2019 estimate | 21288.9 | 1.1254 | 1.1111 | 1.0898 | 1.115 | 1.1113 | 1.1112 | 1.1116 | 1.1603 | 1.1254 | 1.1489 | 1.129 | 1.0672 | 1.0624 | 1.0843
2020 estimate | 22409.7 | 1.1483 | 1.1357 | 1.1115 | 1.1403 | 1.1362 | 1.1361 | 1.1366 | 1.1961 | 1.1483 | 1.1723 | 1.1527 | 1.0884 | 1.084 | 1.1064
2021 estimate | 23557.8 | 1.1712 | 1.1608 | 1.1338 | 1.1658 | 1.1618 | 1.1617 | 1.1622 | 1.2315 | 1.1712 | 1.1958 | 1.1757 | 1.1091 | 1.1057 | 1.1285
2022 estimate | 24753.3 | 1.1948 | 1.1867 | 1.1566 | 1.1922 | 1.1883 | 1.1882 | 1.1886 | 1.2697 | 1.1948 | 1.2199 | 1.1994 | 1.1311 | 1.128 | 1.1513
2023 estimate | 26006.8 | 1.2188 | 1.2131 | 1.1797 | 1.219 | 1.2152 | 1.2151 | 1.2154 | 1.3089 | 1.2188 | 1.2443 | 1.2235 | 1.1531 | 1.1506 | 1.1744
2024 estimate | 27325.7 | 1.2433 | 1.2399 | 1.2035 | 1.2462 | 1.2427 | 1.2427 | 1.243 | 1.3505 | 1.2433 | 1.2693 | 1.248 | 1.1758 | 1.1737 | 1.198
Note: Constant dollar research and development outlays are based on the GDP (chained) price index.

## TravelTime-data
Travel Time Data
This sheet gives the results of the traffic analysis for use in the travel time savings benefits calculations.
|  | 2025 |  |  |  |  | 2040 |  |  |  |  | 2045
| Peak Period | Traffic Volume | No Build TT, secs | Build TT, secs | TT Savings, secs | VHT Savings | Traffic Volume | No Build TT, secs | Build TT, secs | TT Savings, secs | VHT Savings | Traffic Volume | No Build TT, secs | Build TT, secs | TT Savings, secs | VHT Savings
Northbound | AM | 2806.895 | 488.317 | 465.717 | 22.6 | 17.6211 | 2904.5856 | 495.617 | 496.617 | -1 | -0.80683 | 2853.3908 | 496.517 | 462.117 | 34.4 | 27.2657
| PM | 6007.0812 | 612.917 | 499.417 | 113.5 | 189.3899 | 6450.6055 | 652.717 | 549.317 | 103.4 | 185.2757 | 6441.7083 | 649.117 | 574.317 | 74.8 | 133.8444
Southbound | AM | 3241.4835 | 548.017 | 428.617 | 119.4 | 107.5092 | 3434.1562 | 562.217 | 393.217 | 169 | 161.2146 | 3378.6908 | 563.517 | 379.617 | 183.9 | 172.5948
| PM | 3913.6185 | 460.917 | 416.617 | 44.3 | 48.1593 | 4311.1751 | 465.217 | 455.917 | 9.3 | 11.1372 | 4246.9007 | 464.917 | 456.417 | 8.5 | 10.0274
[6 empty] | 2025 |  |  |  |  | 2040 |  |  |  |  | 2045
NB+SB | AM+PM | Daily VHT Savings |  |  |  | 362.6794 |  |  |  |  | 356.8207 |  |  |  |  | 343.7323
Note: AM Peak is from 6am-9am. PM Peak is from 4pm-7pm
Annualization Factor: 260
BCA will also assume that VHT savings is based on existing/projected demand (does not include impacts due to induced traffic)
Year | Total Person Trip | Total Vehicle Trip | Auto Occupancy Rate
2020 | 16692014.3298 | 12624335.8672 | 1.3222 |  | Total Vehicle Trip: | LOV w/o truck + HOV
2025 | 18245016.9704 | 13792459.4081 | 1.3228 |  | Total Person Trip: | DA+SR2GP+SR2HOV+SR3GP+SR3HOV
2030 | 19883077.7546 | 15013960.6902 | 1.3243 |  | Auto Occupancy Rate: | Total Person Trip / Total Vehicle Trip
2040 | 22893267.522 | 17313672.63 | 1.3223
2045 | 23274156.5785 | 17286269.9392 | 1.3464

## EmissionFactors
Emissions Data
This sheet gives the sources and data points used in the emissions savings benefits analysis.
Auto Idling Emissions Reduction
|  | gas-car | gas-light trucks/SUVs/vans | gas-heavy truck | diesel-car | diesel-light trucks/SUVs/vans | diesel-heavy truck
Pollutant | Units | LDGV | LDGT | HDGV | LDDV | LDDT | HDDV | MC | Weighted Average
VOC | g/hr | 2.683 | 4.043 | 6.495 | 1.373 | 2.72 | 3.455 | 19.153 | 3.0997
THC | g/hr | 3.163 | 4.838 | 7.26 | 1.353 | 2.68 | 3.503 | 21.115 | 3.6037
CO | g/hr | 71.225 | 72.725 | 151.9 | 7.018 | 5.853 | 25.628 | 301.075 | 58.8671
NOx | g/hr | 3.515 | 4.065 | 5.33 | 2.69 | 3.705 | 33.763 | 1.625 | 3.6715
PM2.5 | Units: g/hr
PM10 | Units: g/hr
Share | LDGV: 40%; LDGT: 40%; LDDV: 10%; LDDT: 10% | 100%
Source: "Idling Vehicle Emissions for Passenger Cars, Light-Duty Trucks, and Heavy-Duty Trucks Emission Facts", EPA420-F-08-205, October 2008
Note: Analysis only for light-duty vehicles
Note: Assume PM 10 (diameter 10 micrometer or less); PM 2.5 (diameter < 2.5 micrometer)
PM Per Gallon of Gasoline (Passenger Cars) | Units: PM10; LDGV: PM2.5
PM per mile (g) | Units: 0.0044; LDGV: 0.0041 |  | Source: "Idling Vehicle Emissions for Passenger Cars, Light-Duty Trucks, and Heavy-Duty Trucks Emission Facts", EPA420-F-08-205, October 2008
Gasoline consumption per mile (gal) | Units: 0.04149; LDGV: 0.04149
PM Per Gallon (g) | Units: 0.10605; LDGV: 0.098819
Source: "Average Annual Emissions and Fuel Consumption for Gasoline-Fueled Passenger Cars and Light Trucks", EPA420-F-08-024, October 2008
See table: Average Emissions and Fuel Consumption for Passenger Cars
PM Per Gallon of Gasoline (Light Duty Trucks) | Units: PM10; LDGV: PM2.5
PM per mile (g) | Units: 0.0049; LDGV: 0.0045
Gasoline consumption per mile | Units: 0.0578; LDGV: 0.0578
PM Per Gallon (g) | Units: 0.084775; LDGV: 0.077855
Source: "Average Annual Emissions and Fuel Consumption for Gasoline-Fueled Passenger Cars and Light Trucks", EPA420-F-08-024, October 2008
See table: Average Emissions and Fuel Consumption for Light-Duty Trucks
Fuel Consumption Efficiency
Vehicle Type | Units: Engine Size (liters); LDGV: Idling Fuel Use (GAL/HR WITH NO LOAD)
Compact Sedan | Units: 2; LDGV: 0.16
Large Sedan | Units: 4.6; LDGV: 0.39
Source: Fact #861 February 23, 2015 Idle Fuel Consumption for Selected Gasoline and Diesel Vehicles
http://energy.gov/eere/vehicles/fact-861-february-23-2015-idle-fuel-consumption-selected-gasoline-and-diesel-vehicles
Particulate Matter
PM 2.5 Per Hour | Units: 0.024293
PM 10 Per Hour | Units: 0.026238
Grams of CO2 per Gallon of Gasoline | Units: 8887
Gallons per Hour | Units: 0.275
Grams of CO2 per Hour | Units: 2443.925
Source: Greenhouse Gas Emissions from a Typical Passenger Vehicle, EPA
http://nnsa.energy.gov/sites/default/files/nnsa/08-14-multiplefiles/EPA%202011c.pdf
Annual Emission Avoided (tons)
grams per short ton | Units: 907185
grams per metric ton | Units: 1000000
Table VIII-16, "Economic Values Used for Benefits Computations (2010 dollars)"
Value of Emissions Reduced | Units: 2017$; LDGV: 2019$; LDGT: Unit
Carbon Monoxide (CO) | Units: 0; LDGV: 0; LDGT: $/short ton
Volatile Organic Compounds (VOC) | Units: 2000; LDGV: 2065.304; LDGT: $/short ton
Nitrogen Oxides (NOx) | Units: 8300; LDGV: 8571.0114; LDGT: $/short ton
Particulate Matter (PM) | Units: 377800; LDGV: 390135.9172; LDGT: $/short ton
Sulfur Dioxide (SO2) | Units: 48900; LDGV: 50496.6817; LDGT: $/short ton
Carbon Dioxide | Units: varies; LDGV: varies; LDGT: $/metric ton
Source: Corporate Average Fuel Economy for MY2017-MY2025 Passenger Cars and Light Trucks (August 2012), page 922
http://www.nhtsa.gov/staticfiles/rulemaking/pdf/cafe/FRIA_2017-2025.pdf
Note: The Resource Guide converts these values into 2017 dollars.
Source: Benefit-Cost Analysis (BCA) Guidance for Discretionary Grant Programs, December 2018
https://www.transportation.gov/sites/dot.gov/files/docs/mission/office-policy/transportation-policy/14091/benefit-cost-analysis-guidance-2018.pdf